## Sheet1
Week | ML API | Difficulty
5/16/2021 | Create spreadsheet for project planning | Medium
| Create Trello board | Easy
| Create Github repo | Easy
5/23/2021 | Create Cloud Shell environnement | Easy
| Generate and upload SSH keys to Github | Easy
| Create Project Scaffolding | Easy
| Test project setup | Easy
5/30/2021 | Configure GitHub Actions | Hard
| Testing Github Actions configuration | Easy
2021-06-06 | Get the Flask starter code | Easy
| Create new Azure DevOps project | Easy
| Create Azure App Service | Easy
| Setup Continuous Delivery with Azure Pipelines | Hard
| Test Prediction API | Easy
6/13/2021 | Documentation of the project | Medium
| Create architectural diagram | Medium
6/20/2021 | Demo of the project | Hard
Goals
ML API
Logging
DevOps
Testing
Agile project management
Quarterly planning | Submit the project for review
Yearly planning | Review the project and make sure everything is working as expected